## Project information
Customer | MxLP/N | Platform | Application | OS | Market | Forecast | Priority | SCH review | PCB review | Sample time | PP | MP | Status | Action Item | Customer contact | 原始中文
Realbom | XRV1414 | RK3288 SoC | POS,KOISK | Android 9.1 | KOREA, North American | 100 K/Y | High | DONE | DONE | Finished in 2021 | Finished in 2021 | Finished in 2021 | MP | EXAR APK (Android_usb_to_serial_app_Ver_1C) The default node name of xr21v1414 driver is ttyxrusb, Open Exar APK, and then click Connect. APK will crash. Then the ADB shell enters to view the device information LS dev, and the drive node ttyxrusb disappears The judgment is: There is a problem with the Exar APK. The xrdriver part of the APK cannot see the source code and is encapsulated. You need to find the exra original factory to update the APK or replace it with another APK for testing. The serial port can be used normally with our others APK, which means that the driver should be OK. The serial port cannot be used normally only with the Exar APK . What is the Linux version? Which version of Exar driver is used? Android 9 , Kernal 4.x / exar 3.6 | Email: zhourj@realbom.com;hongfeng@realbom.com Jim /洪丰 PM/项目经理 18088883998 深圳市锐宝智联信息有限公司 ShenZhen Realbom Intellitech CO.,LTD 地址:深圳市宝安区石岩街道塘头一号路创维创新谷5A栋9层 Add:9/F, Building 5# A, Chuangwei Innovation Valley, No.1 Tangtou Road, Shiyan Street, Baoan District, Shenzhen，Guangdong ，China Web: www.realbom.com | EXAR APK XR21V1414驱动默认节点名为ttyXRUSB 打开EXAR APK，然后再点击connect按键，apk会崩溃，然后adb shell进入查看设备信息ls dev，出现驱动节点ttyXRUSB消失 判定是： 是ExarUSB 这个APK有问题，APK里面XRDriver这部分是看不到源码的，被封装起来。 需要找Exra原厂更新适配的APK，或者换一个APK测试。 linux版本是？用的是exar哪个版本的驱动？ Android 9 , Kernal 4.x / exar 3.6 用我们自己的APK是可以正常使用串口的，也就是说驱动应该是OK的。 只是用exar这个APK，不能正常使用串口.

## Alex Liang (hidden)
Customer | MxLP/N | Platform | Application | OS | Market | Forecast | Priority | JIRA Track | SCH review | PCB review | Sample time | PP | MP | Status | Action Item | Customer contact
Hisense | MXL254 | RTD1319 | DVB-C |  | Taiwan |  |  |  | done | done | November |  |  | assemble sample board | 协助客户调试 | Sun Shoujun 18563917912
SDMC | MXL248 | S905 | DVB-C | android | India |  |  |  | done | done | August | Sept | Oct | MP | 完善软件待机功能 | Zoau：15013526255
SDMC | MXL691 | S905 | ATSC | android | America |  |  |  | done | done | November 30th |  |  | test sample board | 协助客户测试 | Zoau：15013526255
Konka | MXL248 | S805 | DVB-C | android | India |  |  |  | done | done | Oct |  |  | test sample board | 协助客户测试 | Wang xueru 0755 26608866-6882
Konka | MXL248 | S905 | DVB-C | android | India |  |  |  | done | done | November |  |  | assemble sample board | 协助客户调试 | Wang xueru 0755 26608866-6882
SMIT | MXL248 | SM1685 | DVB-C | linux | China |  |  |  | done | done | November |  |  | Debug | 协助客户调试插拔信号偶尔不能恢复问题；以及查询tuner信号状态小概率返回fail问题 | Zhichun Li 18566220237

## jiagui Zheng (hidden)
Customer | MxLP/N | Platform | Application | OS | Market | Forecast | Priority | JIRA Track | SCH review | PCB review | Sample time | PP | MP | Status | Action Item | Customer contact
Skyworth | MXL248-AM-R | Hi3798MV200 | STB |  | china |  | A |  | 2019-10-29 | 2019-11-29 | 2019-11-05 |  |  | test | 2AGHF12(Hi3798MV200+MxL248) | 谭栋转孔华杰 袁腾
Skyworth | MXL214-CF-R | HI3798MV200 | STB |  | Taiwan |  | A |  | 2019-10-10 | 2019-10-16 |  |  |  | test/Modify PCB | 2AGHD33B（HI3798MV200+MxL214）台湾项目 | 谭栋转杨令
Skyworth | MxL608-AG-T | HI3796 | DBS_STB |  | china |  | C |  | 2019-09-15 | 2019-09-15 |  |  |  | Such as the tender | 2AGT100(HI3796+MXL608)国内第四代直播星 | 刘武
Skyworth | MXL248-AM-R | S905X | STB |  | India |  | A |  | 2019-08-15 | 2019-08-15 |  |  |  | test/Modify PCB | 2AHY40B(S905X+MXL248X2)印度项目 | 孙昌伟
Skyworth | MXL248-AM-R | S905X | STB |  | Mexico and Taiwan |  | A |  | 2019-07-15 | 2019-07-20 |  |  |  | Mass production, | 2AHY40A(S905X+MxL608 +MXL248)综合项目 | 杨宇鹏
Skyworth | MxL608-AG-T | M3711 | STB |  | India |  | A |  | 2019-05-20 | 2019-05-20 |  |  |  | PP | 2AHCJ07(M3711+MXL608)印度项目 | 邓怡谨
Skyworth | MXL254-AF-R | S805 | STB |  | India |  | A |  | 2019-05-15 | 2019-05-25 |  |  |  | test/PP | HPA18(AmlogicS805X+MxL254)印度项目 | 莫春建
ShenZhen JiuZhou Electric Co.,Ltd. | MXL683-AF-R | S905X | STB |  | Philippines |  | B |  | 2019-10-20 | 2019-10-29 | 2019-11-03 |  |  | EV sample has been sent to the customer for testing | DTT9719(S905+MXL683 )菲律宾项目 | 胡磊
ShenZhen JiuZhou Electric Co.,Ltd. | MXL254-AF-R | RTD1611 | STB |  | India |  | A |  | 2019-11-01 | 2019-11-03 | 2019-10-03 |  |  | debug | DTC2141(RTD1611+MxL254 ) nagra _印度ICNCL项目 | 熊金林
ShenZhen JiuZhou Electric Co.,Ltd. | MxL608-AG-T | (Hi3716MV430 | STB |  | Malaysia |  | B |  | 2019-10-15 | 2019-10-18 |  |  |  | EV sample has been sent to the customer for testing | DTT9433V110MB(Hi3716MV430+MXL608)马来西亚T2项目 | 陈远馨/廖善真
ShenZhen JiuZhou Electric Co.,Ltd. | MXL248-AM-R | S905X | STB |  | Russia |  | B |  | 2019-07-10 | 2019-07-29 | 2019-07-29 |  |  | promotion | S905X+ MxL248俄罗斯项目 | 胡磊 杨阳
changhong | MxL608-AG-T | S905X | STB |  | Russia |  | A |  | 2019-08-20 | 2019-08-29 |  |  |  | Mass production, | S905X+MxL608 俄罗斯T2项目 | 岳文强
changhong | MXL248-AM-R | S905X | STB |  | Europe and America |  | A |  | 2019-08-27 | 2019-08-20 | 2019-09-10 |  |  | sample has been sent to the customer for testing | S905X+MxL248欧美项目 | 杨显江
CVTE | MXL661-AG-R | AmlogicT972 | TV |  | Southeast Asia |  | A |  | 2019-10-15 | 2019-10-15 |  |  |  | debug | TP.ATM972.PB733（T9720+MXL661)DTMB 4K项目 | 龙树东
CVTE | MXL661-AG-R | MS3663W-V53 | TV |  | china |  | A |  | 2019-09-15 | 2019-09-15 |  |  |  | Mass production | TPD.MS3663W.PB702-V53（MS3663W+MXL661)长虹项目 | 蒋勇 黄小华 李辉

## Yuexin Lin (hidden)
Customer | MxLP/N | Platform | Application | OS | Market | Forecast/y | Priority | JIRA Track | SCH review | PCB review | Sample time | PP | MP | Status | Action Item | Customer contact
JIuzhouTech | MXL267 | Intel Puma6 | docssis | linux | beijing | 50k |  |  |  |  | 2019-12-15 | Q2 |  | Testing |  | HeYin 13778069340 heying@jiuzhoutech.com
JIuzhouTech | MXL267 | Intel Puma6 | docssis | linux | Korea | / |  |  |  |  | 2019-01-01 | Q2 |  | Testing |  | HeYin 13778069340 heying@jiuzhoutech.com
JIuzhouTech | Mxl214 | Hi3798 | STB 8K | linux | China | / |  |  |  |  | 2019-01-01 | February 30, 2019 |  | Design |  | zhangweidong 15883757074 zhangweidong@jiuzhoutech.com
JIuzhouTech | Mxl214 | Hi3798 | STB | linux | Guangxi | / |  |  |  |  | 2019-01-01 | / |  | Testing |  | zhangweidong 15883757074 zhangweidong@jiuzhoutech.com
JIuzhouTech | Mxl214 | Hi3798 | STB | linux | Jiangsu | / |  |  |  |  | 2019-01-01 | Q2 |  | Testing |  | Penghonsong 13350969420
JIuzhouTech | Mxl214 | Hi3798 | STB | linux | Shandong | 100K |  |  |  |  | 2019-01-01 | 2019-03-01 |  | Design |  | liuwen@jiuzhoutech.com 18009082181
JIuzhouTech | Mxl608 | Hi3798 | STB | linux | Guangdong | 300K |  |  |  |  | 2019-01-01 | Q2 |  | Design |  | liuwen@jiuzhoutech.com 18009082181
Newland | Mxl608 | Gx3203 | STB | linux | South America; | 300K |  |  |  |  | Nov-2019 |  | 2019-01-01 | Testing |  | wangzheng@newland.cn 15818665217
Newland | Mxl608 | Gx3213 | STB | linux | Europe | 200K |  |  |  |  | 2019-12-15 | Q2 |  | Testing |  | zhaohq@newland.cn 18665376595
Newland | Mxl608 | HI3716MV430 | STB | linux | Europe | 200K |  |  |  |  | 2019-12-15 | Q2 |  | Testing |  | zhaohq@newland.cn 18665376595
National Chip | Mxl608 | Gx6701 and Gx6702 | STB | linux | Russia | / |  |  |  |  | 2019-12-15 | Q3 |  | Testing |  | Luoliguo 13892245040
Quanzhou TDX | MXl683 | CS8001 montage | STB | linux | Philippines | / |  |  |  |  | 2019-12-15 | / |  | Testing |  | Marvin Chen cxb@qztdx.com 159-5928-8044
Mico | Mxl608 | Ali2822 | STB | linux | Europe | 300k |  |  |  |  | 2019-12-15 | Q2 |  | Testing |  | dunchong.jiang@micoelectric.com 181 2887 9338
szmtc | MxL608 | Hi3798 | STB | linux | Africa | / |  |  |  |  | 2019-12-15 | Q3 |  | Testing |  | gang.li@szmtc.com.cn 130 5815 6352
szmtc | MXl683 | M3823 | STB | linux | Salvatore | / |  |  |  |  | 2019-12-15 |  |  | Software development |  | ghl@szmtc.com.cn 0755-33614125
szmtc | Mxl683 | AliM3721 | STB | linux | Brazil | / |  |  |  |  | 2019-12-15 | Q3 |  | Testing |  | gang.li@szmtc.com.cn 130 5815 6352
szmtc | MxL541 | HI3798Mv200 | STB | linux | Korea | / | [5 empty] | 2019-12-15 | / | Testing |  | fei.tan@szmtc.com.cn18682100940
Guang Mao | MXl683 | CS8001 montage | STB | linux | Philippines | / |  |  |  |  | 2019-01-01 |  |  |  |  | chen.sy@sxgm.com.cn 15899898405
justek | Mxl608 | Hi3798 | STB | linux | Europe | / |  |  |  |  | 2019-01-01 | Q2 |  | Testing |  | JeffQiu@justek.tv 15559032898
Radio | MxL267D | Puma6 | docssis | linux | Africa | / |  |  |  |  | / |  |  |  |  | tanpei@radiotech.cn 18019569771, Docssis 8月开案，G.hn 4月开案，寄了样品客户不愿告诉项目信息
Radio | (88LX2720+88LX5152) | WAVE2 | G.hn |  | global market | /